{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["VVVVVa","Sheet1","Sheet2"],"not_rendered":{"charts":1,"external_links":1,"defined_names":2},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"VVVVVa","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"hidden":true,"flags":["formulas_cached_only"]}

{"sheet":"Sheet1","index":1,"n_rows":18,"n_cols":18,"rows_kept":18,"merged":[[0,0,0,17],[1,0,1,17],[3,0,4,0],[3,1,3,5],[3,6,3,17]],"flags":["formulas_cached_only"]}
["北京某危改东二区塔台、住宅楼工程劳动力组织计划"]
["（劳动力总控计划）"]
[]
["工种（人）","2000年",{"$nulls":4},"2001年"]
[null,8,9,10,11,12,1,2,3,4,5,6,7,8,9,10,11,12]
["木工",6,20,320,320,320,320,320,320,250,250,250,250,160,100,60,40,20]
["钢筋工",20,160,280,280,280,280,280,280,30,20,10,10,0,0,0,0,0]
["砼工",20,30,60,60,60,60,60,60,30,20,20,20,20,20,20,10,10]
["架子工",15,20,40,40,40,40,40,40,40,40,40,40,40,40,30,30,15]
["瓦工",15,20,30,30,30,30,30,80,80,80,80,80,50,30,30,30,10]
["防水工",0,30,0,30,30,30,30,30,40,20,10,10,0,0,0,0,0]
["力工",20,20,30,30,30,0,0,30,40,40,40,40,40,40,40,40,20]
["电工",4,4,6,6,6,6,6,6,6,6,6,6,6,6,4,4,4]
["焊工",4,8,8,8,8,8,8,8,8,8,8,6,6,4,4,4,4]
["油漆工",0,4,4,4,4,4,4,4,60,60,60,60,60,60,40,20,10]
["水、暖工",0,0,15,20,20,20,20,20,100,120,120,120,120,120,80,50,30]
["电气工",0,0,15,20,20,20,20,20,80,80,100,100,100,80,80,80,20]
["总计",104,316,808,848,848,818,818,898,764,744,744,742,602,500,388,308,143]

{"sheet":"Sheet2","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}